## Sheet1
action_field_id | action_field | action_field_measure_id | action_field_measure | source | PO | BO | committments | source_simple | expected_by | status | __PowerAppsId__
10 | SEAMLESS JOURNE, DIGITAL BUSINESS AND AGENCY MODEL READINESS | 10a | ONE.CRM Campaign, Lead & Request/Complaint | 2023 | R. Vitorio | R. Vitorio | Implementation of CRM instance: Sales Cloud and Marketing Cloud | 2023 | H1 2023 | Pending | 6zECLr466Kk
10 | SEAMLESS JOURNE, DIGITAL BUSINESS AND AGENCY MODEL READINESS | 10a | ONE.CRM Campaign, Lead & Request/Complaint | 2023 | R. Vitorio | R. Vitorio | Marketing Automation start of operations | 2023 | H1 2023 | Pending | xZPxxOPviMA
10 | SEAMLESS JOURNE, DIGITAL BUSINESS AND AGENCY MODEL READINESS | 10a | ONE.CRM Campaign, Lead & Request/Complaint | 2023 | R. Vitorio | R. Vitorio | Enrolment, Renewals and Surveys emailings | 2023 | H1 2023 | Pending | a5D_w-gOcWY
10 | SEAMLESS JOURNE, DIGITAL BUSINESS AND AGENCY MODEL READINESS | 10a | ONE.CRM Campaign, Lead & Request/Complaint | 2023 | R. Vitorio | R. Vitorio | Emailing based on Consent | 2023 | H2 2023 | Pending | X0P24DHNzcs
10 | SEAMLESS JOURNE, DIGITAL BUSINESS AND AGENCY MODEL READINESS | 10a | ONE.CRM Campaign, Lead & Request/Complaint | 2023 | R. Vitorio | R. Vitorio | Request MyCUPRA App integration | 2023 | H2 2023 | Pending | UHqquHnI6mM
10 | SEAMLESS JOURNE, DIGITAL BUSINESS AND AGENCY MODEL READINESS | 10a | ONE.CRM Campaign, Lead & Request/Complaint | 2023 | R. Vitorio | R. Vitorio | Request Private area integration | 2023 | H2 2023 | Pending | hde-9_W1KoY
10 | SEAMLESS JOURNE, DIGITAL BUSINESS AND AGENCY MODEL READINESS | 10c | UX private area | New from DPC Feb. 2023 | I. Jover | I. León | Dashboard redesign. | New from DPC Feb. 2023 | H1 2023 | Pending | xe_UuNBYmms
10 | SEAMLESS JOURNE, DIGITAL BUSINESS AND AGENCY MODEL READINESS | 10c | UX private area | New from DPC Feb. 2023 | I. Jover | I. León | UX/UI for appointment management. | New from DPC Feb. 2023 | H1 2023 | Done | 1SNNY0PhvbY
10 | SEAMLESS JOURNE, DIGITAL BUSINESS AND AGENCY MODEL READINESS | 10c | UX private area | New from DPC Feb. 2023 | I. Jover | I. León | Order tracking improvement with AVP videos. | New from DPC Feb. 2023 | H1 2023 | Done | zN0v-PQPIPs
10 | SEAMLESS JOURNE, DIGITAL BUSINESS AND AGENCY MODEL READINESS | 10c | UX private area | New from DPC Feb. 2023 | I. Jover | I. León | Private area strategy. | New from DPC Feb. 2023 | H1 2023 | Pending | ctLhVw2hk5U
10 | SEAMLESS JOURNE, DIGITAL BUSINESS AND AGENCY MODEL READINESS | 10c | UX private area | New from DPC Feb. 2023 | I. Jover | I. León | General UX improvements | New from DPC Feb. 2023 | H2 2023 | Pending | T2IwYFDgDlg
10 | SEAMLESS JOURNE, DIGITAL BUSINESS AND AGENCY MODEL READINESS | 10d | UX CUPRA web | New from DPC Feb. 2023 | A. Losada (From CODE) | I. León | New FAQ seccion, SEO Friendly | New from DPC Feb. 2023 | H1 2023 | Done | P76Rhl_RMZ4
10 | SEAMLESS JOURNE, DIGITAL BUSINESS AND AGENCY MODEL READINESS | 10d | UX CUPRA web | New from DPC Feb. 2023 | A. Losada (From CODE) | I. León | Accesibility option in footer | New from DPC Feb. 2023 | H1 2023 | Pending | LjlKo8vDs58
10 | SEAMLESS JOURNE, DIGITAL BUSINESS AND AGENCY MODEL READINESS | 10d | UX CUPRA web | New from DPC Feb. 2023 | A. Losada (From CODE) | I. León | New navigation menu | New from DPC Feb. 2023 | H1 2023 | Pending | H9Lo5_xgS00
10 | SEAMLESS JOURNE, DIGITAL BUSINESS AND AGENCY MODEL READINESS | 10d | UX CUPRA web | New from DPC Feb. 2023 | A. Losada (From CODE) | I. León | General UX improvements | New from DPC Feb. 2023 | H2 2023 | Pending | iIuaoiOfhVs
10 | SEAMLESS JOURNE, DIGITAL BUSINESS AND AGENCY MODEL READINESS | 10d | UX CUPRA web | New from DPC Feb. 2023 | A. Losada (From CODE) | I. León | DCC unification with GFA (deayed from H1 2023) | New from DPC Feb. 2023 | H2 2023 | Pending | YgaT8ZqmCmk
10 | SEAMLESS JOURNE, DIGITAL BUSINESS AND AGENCY MODEL READINESS | 10e | UX eCommerce | New from DPC Feb. 2023 | M. Gómez | T. Garcia | New Car Configurator experience (Zenit): UX/UI definition | New from DPC Feb. 2023 | H1 2023 | Pending | EI-IZnOycac
10 | SEAMLESS JOURNE, DIGITAL BUSINESS AND AGENCY MODEL READINESS | 10e | UX eCommerce | New from DPC Feb. 2023 | M. Gómez | T. Garcia | New Car Configurator experience (Zenit): Architecture definition | New from DPC Feb. 2023 | H1 2023 | Pending | YhQ3Vd6wXi0
10 | SEAMLESS JOURNE, DIGITAL BUSINESS AND AGENCY MODEL READINESS | 10e | UX eCommerce | New from DPC Feb. 2023 | M. Gómez | T. Garcia | Display for MyCUPRA APP functions in Phone main screen | New from DPC Feb. 2023 | H1 2023 | Pending | wdVtI8BVzMQ
10 | SEAMLESS JOURNE, DIGITAL BUSINESS AND AGENCY MODEL READINESS | 10e | UX eCommerce | New from DPC Feb. 2023 | M. Gómez | T. Garcia | New Car Configurator experience (Zenit): Development | New from DPC Feb. 2023 | H2 2023 | Pending | h7RMCh83d0U
10 | SEAMLESS JOURNE, DIGITAL BUSINESS AND AGENCY MODEL READINESS | 10e | UX eCommerce | New from DPC Feb. 2023 | M. Gómez | T. Garcia | New Car Configurator experience (Zenit): Go Live 1 market | New from DPC Feb. 2023 | H2 2023 | Pending | czmVGVjpENE
11 | MyCUPRA APP AS MAIN DIGITAL PLATFORM FOR OWNERS | 11a | Technical performance | New from DPC Feb. 2023 | E. Parrilla | A. Solves | Improve product performance regarding response times and APP launch. | New from DPC Feb. 2023 | H1 2023 | Pending | owSypDET5zQ
11 | MyCUPRA APP AS MAIN DIGITAL PLATFORM FOR OWNERS | 11a | Technical performance | New from DPC Feb. 2023 | E. Parrilla | A. Solves | Improve product quality for minimizing regression errors and ensuring futures features scalability. | New from DPC Feb. 2023 | H1 2023 | Pending | uNzjKKajDX0
11 | MyCUPRA APP AS MAIN DIGITAL PLATFORM FOR OWNERS | 11a | Technical performance | New from DPC Feb. 2023 | E. Parrilla | A. Solves | Slowness improvements. | New from DPC Feb. 2023 | H1 2023 | Pending | 6z9EUa5ZsAQ
11 | MyCUPRA APP AS MAIN DIGITAL PLATFORM FOR OWNERS | 11a | Technical performance | New from DPC Feb. 2023 | E. Parrilla | A. Solves | TBD according to technical spike | New from DPC Feb. 2023 | H2 2023 | Pending | WTdiSGn5aFo
11 | MyCUPRA APP AS MAIN DIGITAL PLATFORM FOR OWNERS | 11b | UX app | New from DPC Feb. 2023 | E. Parrilla | A. Solves | UI/UX target picture definition. | New from DPC Feb. 2023 | H1 2023 | Pending | c2c_JYxEinM
11 | MyCUPRA APP AS MAIN DIGITAL PLATFORM FOR OWNERS | 11b | UX app | New from DPC Feb. 2023 | E. Parrilla | A. Solves | Implement a set of strategic quick wins to improve charging process and users' feedback UX. | New from DPC Feb. 2023 | H1 2023 | Pending | uJ0yqeV4XGc
11 | MyCUPRA APP AS MAIN DIGITAL PLATFORM FOR OWNERS | 11b | UX app | New from DPC Feb. 2023 | E. Parrilla | A. Solves | TBD according to UI/UX target picture defination. | New from DPC Feb. 2023 | H2 2023 | Pending | HK8bkHErf6U
11 | MyCUPRA APP AS MAIN DIGITAL PLATFORM FOR OWNERS | 11c | Legacy / support car SOP | New from DPC Feb. 2023 | A. Solves | J. Espinalt | MOD 3 integration | New from DPC Feb. 2023 | H1 2023 | Pending | 4YsyF4qdOyc
11 | MyCUPRA APP AS MAIN DIGITAL PLATFORM FOR OWNERS | 11c | Legacy / support car SOP | New from DPC Feb. 2023 | A. Solves | J. Espinalt | Integration MOD3 UNECE Portfolio within My CUPRA App | New from DPC Feb. 2023 | H2 2023 | Pending | nJttjkKbuQs
11 | MyCUPRA APP AS MAIN DIGITAL PLATFORM FOR OWNERS | 11c | Legacy / support car SOP | New from DPC Feb. 2023 | A. Solves | J. Espinalt | Integration MOD4 UNECE Portfolio within My CUPRA App | New from DPC Feb. 2023 | H2 2023 | Pending | T4rjBNQviP0
12 | IMPROVE DATA BUSINESS VIA | 12a | Data Sharing OEM-FS-NSC | 2023 | R. Vitorio | R. Vitorio | Scope: Leverage FS Data to enhance Loyalty and UpsellingPilot with ES based on OEM data, FS data and Importer's data (within Digital Renewal Scope)One.CRM dedicated budget to define the integration between FS and Brands. Nebertheless, the data scope and legal assessment are still pending (work with Data Sharing Initiative)This initiative was cancelled due to FS ES legal concerns, therefore a campaign will be made directly by FS ES with a creative provided by SEAT and redirected to a SEAT form in order to make the follow up by the brand.Scope: OEM-NSC/Importer (Data Transfer) | 2023 | H1 2023 | Pending | CRkn9QGsMko
12 | IMPROVE DATA BUSINESS VIA | 12a | Data Sharing OEM-FS-NSC | 2023 | R. Vitorio | R. Vitorio | [Data Transfer] Data transfer reshaping: End Points reduction, timming optimization, use Case approach, business as main driver | 2023 | H1 2023 | Done | uwBnJRSNSv4
12 | IMPROVE DATA BUSINESS VIA | 12a | Data Sharing OEM-FS-NSC | 2023 | R. Vitorio | R. Vitorio | [Data Transfer] Technical readiness of 4 use cases (2 use cases Live) | 2023 | H1 2023 | Pending | xP1BAym_3ro
12 | IMPROVE DATA BUSINESS VIA | 12a | Data Sharing OEM-FS-NSC | 2023 | R. Vitorio | R. Vitorio | [Data Transfer] Connection from ES, DE, CH (Spain already connected and starting 1st use case) | 2023 | H1 2023 | Pending | pLYn_pA_PUs
12 | IMPROVE DATA BUSINESS VIA | 12a | Data Sharing OEM-FS-NSC | 2023 | R. Vitorio | R. Vitorio | [FS data] Include the data use case in the Digital Renewal blueprint and depending on the conclusion if the legal assesment bring the ES use case to other markets Data Transfer | 2023 | H2 2023 | Pending | xoi_NOeDvNQ
12 | IMPROVE DATA BUSINESS VIA | 12a | Data Sharing OEM-FS-NSC | 2023 | R. Vitorio | R. Vitorio | [Data Transfer] Markets use cases follow-up | 2023 | H2 2023 | Pending | tibWLwAXSlo
12 | IMPROVE DATA BUSINESS VIA | 12a | Data Sharing OEM-FS-NSC | 2023 | R. Vitorio | R. Vitorio | [Data Transfer]Additional use cases identification | 2023 | H2 2023 | Pending | RalfEA7oaT4
12 | IMPROVE DATA BUSINESS VIA | 12a | Data Sharing OEM-FS-NSC | 2023 | R. Vitorio | R. Vitorio | [Data Transfer] MOD4 Data integration | 2023 | H2 2023 | Pending | eUClmblVTMg
12 | IMPROVE DATA BUSINESS VIA | 12b | Data Optimization Projects | Continuous delivery Ongoing measure. Started in 2022 | F. Amargant / S.Álvarez / I.Única | F. Amargant / S.Álvarez / I.Única | Close SALY, Q-Lant (Phase 2) and Atenea (DNK, FR, UK) | Started in 2022 | H1 2023 | Pending | ZAs7OVW0SaE
12 | IMPROVE DATA BUSINESS VIA | 12b | Data Optimization Projects | Continuous delivery Ongoing measure. Started in 2022 | F. Amargant / S.Álvarez / I.Única | F. Amargant / S.Álvarez / I.Única | Mock up and data access for RITA | Started in 2022 | H1 2023 | Done | pe8ZhxewrPc
12 | IMPROVE DATA BUSINESS VIA | 12b | Data Optimization Projects | Continuous delivery Ongoing measure. Started in 2022 | F. Amargant / S.Álvarez / I.Única | F. Amargant / S.Álvarez / I.Única | Mock up and data access for Q-Data, Polar Express, Absenteeism | Started in 2022 | H1 2023 | Pending | rgWLmlfjJQY
12 | IMPROVE DATA BUSINESS VIA | 12b | Data Optimization Projects | Continuous delivery Ongoing measure. Started in 2022 | F. Amargant / S.Álvarez / I.Única | F. Amargant / S.Álvarez / I.Única | Atenea extend to other markets (CH, AT, DE, ES, IT) | Started in 2022 | H2 2023 | Pending | HpqJH2BMnMU
12 | IMPROVE DATA BUSINESS VIA | 12b | Data Optimization Projects | Continuous delivery Ongoing measure. Started in 2022 | F. Amargant / S.Álvarez / I.Única | F. Amargant / S.Álvarez / I.Única | Release Q-Data, Polar Express, Absenteeism & Rita | Started in 2022 | H2 2023 | Pending | FGtdrK5J_OM
12 | IMPROVE DATA BUSINESS VIA | 12b | Data Optimization Projects | Continuous delivery Ongoing measure. Started in 2022 | F. Amargant / S.Álvarez / I.Única | F. Amargant / S.Álvarez / I.Única | Mock up and data access for Steel Risk project | Started in 2022 | H2 2023 | Pending | cSvIJ6PdvCY
12 | IMPROVE DATA BUSINESS VIA | 12b | Data Optimization Projects | Continuous delivery Ongoing measure. Started in 2022 | F. Amargant / S.Álvarez / I.Única | F. Amargant / S.Álvarez / I.Única | Define 2 more new projects | Started in 2022 | H2 2023 | Pending | b2mSUAgFzEs
12 | IMPROVE DATA BUSINESS VIA | 12c | Data Licensing | Continuous delivery Ongoing measure. Started in 2022 | M. Palma | M. Palma | Approval (DPC 21.02) of 4.screen In-car integration with Location Based Offers (LBO) Webapp. (Pending approval DPC 31.05) | Started in 2022 | H1 2023 | Pending | d6pGU9OM1y0
12 | IMPROVE DATA BUSINESS VIA | 12c | Data Licensing | Continuous delivery Ongoing measure. Started in 2022 | M. Palma | M. Palma | Approval (Q2/23) of Personal Data Enabler integration: Car Data Brokerage (CDB) Webapp. | Started in 2022 | H1 2023 | Pending | tFeztKJS39M
12 | IMPROVE DATA BUSINESS VIA | 12c | Data Licensing | Continuous delivery Ongoing measure. Started in 2022 | M. Palma | M. Palma | Start Revenue sharing for CDB Webapp with 1 data aggregators. (delayed from H1). | Started in 2022 | H2 2023 | Pending | kH7Y4gVcooM
12 | IMPROVE DATA BUSINESS VIA | 12c | Data Licensing | Continuous delivery Ongoing measure. Started in 2022 | M. Palma | M. Palma | Ramp-up Data brokerage revenue of 1 more data consumer. (Delayed to 2024) | Started in 2022 | H2 2023 | Pending | mVzW3-rTvQ8
12 | IMPROVE DATA BUSINESS VIA | 12c | Data Licensing | Continuous delivery Ongoing measure. Started in 2022 | M. Palma | M. Palma | Personal Data Enabler Integration (CDB update + Consent Mgt). | Started in 2022 | H2 2023 | Pending | vEmGzQNPGlc
12 | IMPROVE DATA BUSINESS VIA | 12c | Data Licensing | Continuous delivery Ongoing measure. Started in 2022 | M. Palma | M. Palma | Usage Based Insurance (UBI) UC MVP with MAPFRE live. | Started in 2022 | H2 2023 | Pending | o6gK5-UcYds
12 | IMPROVE DATA BUSINESS VIA | 12c | Data Licensing | Continuous delivery Ongoing measure. Started in 2022 | M. Palma | M. Palma | Go-live 4.screen Integration In-Car (LBO Webapp) in MOD3/MOD4. | Started in 2022 | H2 2023 | Pending | BaM6QKEiVYw
1 | INCREASE CONVERSION RATE VIA | 1a | Entry point qualification (Product offer proposal) | H1 2022 Delayed from 2022 | A. Losada (From CODE) | T. Garcia | Delivery of personalized offers finished | Delayed from 2022 | H1 2023 | Done | VYC8MjZO-aQ
1 | INCREASE CONVERSION RATE VIA | 1a | Entry point qualification (Product offer proposal) | H1 2022 Delayed from 2022 | A. Losada (From CODE) | T. Garcia | Rollout plan to be defined. Target: rollout to 2 markets | Delayed from 2022 | H1 2023 | Pending | 2wIOp9STz1U
1 | INCREASE CONVERSION RATE VIA | 1a | Entry point qualification (Product offer proposal) | H1 2022 Delayed from 2022 | A. Losada (From CODE) | T. Garcia | First rollout market ES. | Delayed from 2022 | H2 2023 | Pending | AsKqMXt3QKo
1 | INCREASE CONVERSION RATE VIA | 1a | Entry point qualification (Product offer proposal) | H1 2022 Delayed from 2022 | A. Losada (From CODE) | T. Garcia | Rollout to other markets | Delayed from 2022 | H2 2023 | Pending | Tx6lR3C0qeo
1 | INCREASE CONVERSION RATE VIA | 1b | Stock Car match | H1 2022 Ongoing measure. Started in 2022 | M. Gómez | T. Garcia | Q2/23 Australia go live. (delayed from Q1/23) | Started in 2022 | H1 2023 | Pending | N5Pvfs-RDtI
1 | INCREASE CONVERSION RATE VIA | 1b | Stock Car match | H1 2022 Ongoing measure. Started in 2022 | M. Gómez | T. Garcia | Build a plan for rollout (ES, FR, UK, IT) in private area & car configurator (pre-requisite availability of VTP) | Started in 2022 | H1 2023 | Pending | QrmKWZ3Pgv4
1 | INCREASE CONVERSION RATE VIA | 1b | Stock Car match | H1 2022 Ongoing measure. Started in 2022 | M. Gómez | T. Garcia | Rollout to markets | Started in 2022 | H2 2023 | Pending | GHk5Na0962M
1 | INCREASE CONVERSION RATE VIA | 1c | Recommendations | H1 2022 Ongoing measure. Started in 2022 | I. León | J. Fernández | Rollout in ES (CW23, delayed from CW05/23). No further rollout foreseen, as rest of markets do not prioritize it (pending local management approval for launching) - go live 2nd of may - delayed until Closed Types is launched | Started in 2022 | H1 2023 | Pending | zRtNiIt2trs
1 | INCREASE CONVERSION RATE VIA | 1c | Recommendations | H1 2022 Ongoing measure. Started in 2022 | I. León | J. Fernández | Review performance of this feature via analytics | Started in 2022 | H1 2023 | Pending | wfF3BGsrfb4
1 | INCREASE CONVERSION RATE VIA | 1c | Recommendations | H1 2022 Ongoing measure. Started in 2022 | I. León | J. Fernández | Improvements Plan to be reviewed | Started in 2022 | H2 2023 | Pending | KSrrd40GRgQ
1 | INCREASE CONVERSION RATE VIA | 1c | Recommendations | H1 2022 Ongoing measure. Started in 2022 | I. León | J. Fernández | Rollout Plan to be reviewed | Started in 2022 | H2 2023 | Pending | 8nTREGq3MCg
1 | INCREASE CONVERSION RATE VIA | 1d | AVP Car Renders | H2 2022 Ongoing measure. Started in 2022 | J. Balaguer | J. Fernández | Ateca, Leon w/ model year (May.'23) | Started in 2022 | H1 2023 | Done | QuAJQst1-O8
1 | INCREASE CONVERSION RATE VIA | 1d | AVP Car Renders | H2 2022 Ongoing measure. Started in 2022 | J. Balaguer | J. Fernández | Web CC Maintenance | Started in 2022 | H1 2023 | Done | WL8LRJcppsA
1 | INCREASE CONVERSION RATE VIA | 1d | AVP Car Renders | H2 2022 Ongoing measure. Started in 2022 | J. Balaguer | J. Fernández | Tavascan Launch | Started in 2022 | H2 2023 | Pending | H-olrjsimFk
1 | INCREASE CONVERSION RATE VIA | 1d | AVP Car Renders | H2 2022 Ongoing measure. Started in 2022 | J. Balaguer | J. Fernández | Jelly Beans | Started in 2022 | H2 2023 | Pending | yTwhWn6P8oo
1 | INCREASE CONVERSION RATE VIA | 1d | AVP Car Renders | H2 2022 Ongoing measure. Started in 2022 | J. Balaguer | J. Fernández | New Model Selection --> pilot in CW with Tavascan (CC lite) | Started in 2022 | H2 2023 | Pending | FnOqiyyE3NI
1 | INCREASE CONVERSION RATE VIA | 1d | AVP Car Renders | H2 2022 Ongoing measure. Started in 2022 | J. Balaguer | J. Fernández | Product details - PI 23.3 | Started in 2022 | H2 2023 | Pending | 0dzrjI9ken4
1 | INCREASE CONVERSION RATE VIA | 1d | AVP Car Renders | H2 2022 Ongoing measure. Started in 2022 | J. Balaguer | J. Fernández | Individualized landing page (Q4) | Started in 2022 | H2 2023 | Pending | KUxxEqCj45E
1 | INCREASE CONVERSION RATE VIA | 1d | AVP Car Renders | H2 2022 Ongoing measure. Started in 2022 | J. Balaguer | J. Fernández | Model Year update | Started in 2022 | H2 2023 | Pending | sY-uIl8eP6s
1 | INCREASE CONVERSION RATE VIA | 1e | Personalization | 2023 | I. León | R. Vitorio | Governance Definition: Portal's team and CRM (Q1/23) | 2023 | H1 2023 | Done | Tiw5JKu4r5o
1 | INCREASE CONVERSION RATE VIA | 1e | Personalization | 2023 | I. León | R. Vitorio | Tactical use cases identification and market's approval | 2023 | H1 2023 | Done | PGkElZyrxEA
1 | INCREASE CONVERSION RATE VIA | 1e | Personalization | 2023 | I. León | R. Vitorio | Brand use cases identification: portal personalization based on IDK UUID (unique user ID) | 2023 | H1 2023 | Done | M4MwpZsEIB0
1 | INCREASE CONVERSION RATE VIA | 1e | Personalization | 2023 | I. León | R. Vitorio | 2 tactical use cases roll out in 4 markets (FR, IT, MX, ES). ES, FR Live in CW22/23. | 2023 | H1 2023 | Pending | ZXD1mR2yha8
1 | INCREASE CONVERSION RATE VIA | 1e | Personalization | 2023 | I. León | R. Vitorio | More use cases to be rolled out in 4 markets (FR, IT, MX, ES) | 2023 | H2 2023 | Pending | TMNe9ZNMIAQ
1 | INCREASE CONVERSION RATE VIA | 1f | Information Architecture | Digital Platforms Strategy 2023 | I. León | I. León | Architecture information definition | Digital Platforms Strategy 2023 | H1 2023 | Done | bQ1sV0SV0_w
1 | INCREASE CONVERSION RATE VIA | 1f | Information Architecture | Digital Platforms Strategy 2023 | I. León | I. León | Information architecture governace model with VM | Digital Platforms Strategy 2023 | H1 2023 | Done | 8fc5H5Ajmt8
1 | INCREASE CONVERSION RATE VIA | 1f | Information Architecture | Digital Platforms Strategy 2023 | I. León | I. León | Migration plan definition | Digital Platforms Strategy 2023 | H1 2023 | Pending | AowcnFWyk6U
1 | INCREASE CONVERSION RATE VIA | 1f | Information Architecture | Digital Platforms Strategy 2023 | I. León | I. León | Content migration | Digital Platforms Strategy 2023 | H2 2023 | Pending | ifPi7fCFNkY
1 | INCREASE CONVERSION RATE VIA | 1g | Brand Universe | Digital Platforms Strategy 2023 | A. Losada (From CODE) | A. Losada (From CODE) | Rollout plan definition | Digital Platforms Strategy 2023 | H1 2023 | Pending | 1jWjI8lapzI
1 | INCREASE CONVERSION RATE VIA | 1g | Brand Universe | Digital Platforms Strategy 2023 | A. Losada (From CODE) | A. Losada (From CODE) | Rollout UK, FR | Digital Platforms Strategy 2023 | H1 2023 | Pending | _1xdPQB5ktY
1 | INCREASE CONVERSION RATE VIA | 1g | Brand Universe | Digital Platforms Strategy 2023 | A. Losada (From CODE) | A. Losada (From CODE) | More rollout markets | Digital Platforms Strategy 2023 | H2 2023 | Pending | 6NoepdyUpHI
1 | INCREASE CONVERSION RATE VIA | 1h | New Homepage | Digital Platforms Strategy 2023 | A. Losada (From CODE) | A. Losada (From CODE) | New home pilot definition | Digital Platforms Strategy 2023 | H1 2023 | Done | jO3eVWylTi4
1 | INCREASE CONVERSION RATE VIA | 1h | New Homepage | Digital Platforms Strategy 2023 | A. Losada (From CODE) | A. Losada (From CODE) | Test implementation in FR | Digital Platforms Strategy 2023 | H1 2023 | Done | 4aBGVMnIIZU
1 | INCREASE CONVERSION RATE VIA | 1h | New Homepage | Digital Platforms Strategy 2023 | A. Losada (From CODE) | A. Losada (From CODE) | Rework based on test result | Digital Platforms Strategy 2023 | H1 2023 | Pending | SExsc2yL3Js
1 | INCREASE CONVERSION RATE VIA | 1h | New Homepage | Digital Platforms Strategy 2023 | A. Losada (From CODE) | A. Losada (From CODE) | Rollout plan definition | Digital Platforms Strategy 2023 | H1 2023 | Pending | rsONyidMfWI
1 | INCREASE CONVERSION RATE VIA | 1h | New Homepage | Digital Platforms Strategy 2023 | A. Losada (From CODE) | A. Losada (From CODE) | More rollout markets | Digital Platforms Strategy 2023 | H2 2023 | Pending | odi7vskwkOI
1 | INCREASE CONVERSION RATE VIA | 1i | New CAR World 2.0 | Digital Platforms Strategy 2023 | A. Losada (From CODE) | A. Losada (From CODE) | UI/UX definition | Digital Platforms Strategy 2023 | H1 2023 | Pending | 8ig7kCf7GkQ
1 | INCREASE CONVERSION RATE VIA | 1i | New CAR World 2.0 | Digital Platforms Strategy 2023 | A. Losada (From CODE) | A. Losada (From CODE) | Content definition | Digital Platforms Strategy 2023 | H1 2023 | Pending | zGYdriAJOXE
1 | INCREASE CONVERSION RATE VIA | 1i | New CAR World 2.0 | Digital Platforms Strategy 2023 | A. Losada (From CODE) | A. Losada (From CODE) | Assest creation (videos, pictures…) | Digital Platforms Strategy 2023 | H1 2023 | Pending | 1-ZK-4OJ4sY
1 | INCREASE CONVERSION RATE VIA | 1i | New CAR World 2.0 | Digital Platforms Strategy 2023 | A. Losada (From CODE) | A. Losada (From CODE) | Components development | Digital Platforms Strategy 2023 | H1 2023 | Pending | 15WsDvD_LYg
1 | INCREASE CONVERSION RATE VIA | 1i | New CAR World 2.0 | Digital Platforms Strategy 2023 | A. Losada (From CODE) | A. Losada (From CODE) | Rollout to markets for commercial release | Digital Platforms Strategy 2023 | H2 2023 | Pending | hVenzYbCXaA
2 | INCREASE CALL-TO-ACTION RATE VIA | 2a | Online test-drive booking | H2 2022 Delayed from 2022 | A. Losada (From CODE) | J. Fernández | New test drive request flow for markets with no real time confirmation | Delayed from 2022 | H1 2023 | Pending | zm0VjZ3F9vs
2 | INCREASE CALL-TO-ACTION RATE VIA | 2a | Online test-drive booking | H2 2022 Delayed from 2022 | A. Losada (From CODE) | J. Fernández | WS test drive concept (C14 17.03) | Delayed from 2022 | H1 2023 | Done | ebFJaIdUKu8
2 | INCREASE CALL-TO-ACTION RATE VIA | 2a | Online test-drive booking | H2 2022 Delayed from 2022 | A. Losada (From CODE) | J. Fernández | Expected delivery in May'23 (pilot FR w/Giravolta) - output exchange pending to be shared | Delayed from 2022 | H1 2023 | Done | 1cstZChYH2I
2 | INCREASE CALL-TO-ACTION RATE VIA | 2a | Online test-drive booking | H2 2022 Delayed from 2022 | A. Losada (From CODE) | J. Fernández | Review solution of NL (WS CW11/23) and potential for rolling it out | Delayed from 2022 | H1 2023 | Done | eNq4UKioUvI
2 | INCREASE CALL-TO-ACTION RATE VIA | 2a | Online test-drive booking | H2 2022 Delayed from 2022 | A. Losada (From CODE) | J. Fernández | 26.04. WS with main markets BO - pending to find a market for real time confirmation test drive | Delayed from 2022 | H1 2023 | Done | kXg5A8bQ_ww
2 | INCREASE CALL-TO-ACTION RATE VIA | 2a | Online test-drive booking | H2 2022 Delayed from 2022 | A. Losada (From CODE) | J. Fernández | Define roll-out plan | Delayed from 2022 | H1 2023 | Pending | 5SfNtBRzWkk
2 | INCREASE CALL-TO-ACTION RATE VIA | 2a | Online test-drive booking | H2 2022 Delayed from 2022 | A. Losada (From CODE) | J. Fernández | Rollout to markets of new test drive request flow with no real time confirmation | Delayed from 2022 | H2 2023 | Pending | gk_iGsaKI_M
2 | INCREASE CALL-TO-ACTION RATE VIA | 2b | a) 3D Remote Experience(AVP) b) Giveaway (AVP) | 2023 | J. Balaguer | J. Fernández | Giveaway: Solution Readiness + Rollout (ES, UK, FR) | 2023 | H1 2023 | Pending | lWbYxsn6TbY
2 | INCREASE CALL-TO-ACTION RATE VIA | 2b | a) 3D Remote Experience(AVP) b) Giveaway (AVP) | 2023 | J. Balaguer | J. Fernández | Track roll-out to dealer network | 2023 | H1 2023 | Pending | GVL3Qquv4Bo
2 | INCREASE CALL-TO-ACTION RATE VIA | 2b | a) 3D Remote Experience(AVP) b) Giveaway (AVP) | 2023 | J. Balaguer | J. Fernández | Development CUPRA Dealer pages3D Remote Experience MVP (Pilot Market TBD) | 2023 | H2 2023 | Pending | WEIoa3BZChU
2 | INCREASE CALL-TO-ACTION RATE VIA | 2b | a) 3D Remote Experience(AVP) b) Giveaway (AVP) | 2023 | J. Balaguer | J. Fernández | Development CUPRA Dealer pagesTrack roll-out to dealer network | 2023 | H2 2023 | Pending | 9rcJ8vxcViM
2 | INCREASE CALL-TO-ACTION RATE VIA | 2b | a) 3D Remote Experience(AVP) b) Giveaway (AVP) | 2023 | J. Balaguer | J. Fernández | Rollout DE (delayed from H1 due to lack of local resources) | 2023 | H2 2023 | Pending | XZcY87yWGyc
3 | IMPROVE ONLINE READINESS AND CUSTOMER SATISFACTION | 3a | Digital assistance - consideration phase | H1 2022 3a / 2023 3b Delayed from 2022 | R. Vitorio | R. Vitorio | Project scope changed due market's lack of interest and resources. Focus only on website FAQ: assessment, configuration and execution to be made for EUR5 | Delayed from 2022 | H1 2023 | Pending | TqYBtyDU12M
3 | IMPROVE ONLINE READINESS AND CUSTOMER SATISFACTION | 3a | Digital assistance - consideration phase | H1 2022 3a / 2023 3b Delayed from 2022 | R. Vitorio | R. Vitorio | Creation of the queries and decision trees. | Delayed from 2022 | H1 2023 | Done | upYCe0xppkU
3 | IMPROVE ONLINE READINESS AND CUSTOMER SATISFACTION | 3a | Digital assistance - consideration phase | H1 2022 3a / 2023 3b Delayed from 2022 | R. Vitorio | R. Vitorio | Benchmark chatbot vendor.Chatbot RFP and selection.Communicatin to markets and feedback gathering. No agreement due to lack of resources from markets.Mitigation plan definitionWebsite requirements.CiC impact assessment - define operations.DRC new requirements. | Delayed from 2022 | H1 2023 | Done | a2exUhovuWk
3 | IMPROVE ONLINE READINESS AND CUSTOMER SATISFACTION | 3a | Digital assistance - consideration phase | H1 2022 3a / 2023 3b Delayed from 2022 | R. Vitorio | R. Vitorio | Development and Rollout of the FAQ in EUR5 | Delayed from 2022 | H2 2023 | Pending | XqmMECNvmY4
3 | IMPROVE ONLINE READINESS AND CUSTOMER SATISFACTION | 3a | Digital assistance - consideration phase | H1 2022 3a / 2023 3b Delayed from 2022 | R. Vitorio | R. Vitorio | Development and Rollout to at least 1 market | Delayed from 2022 | H2 2023 | Pending | cK_txUh4VeY
3 | IMPROVE ONLINE READINESS AND CUSTOMER SATISFACTION | 3b | Retail integration | New from DPC Feb. 2023 | I. León | J. Fernández | CUPRA City Garage website landing | New from DPC Feb. 2023 | H1 2023 | Pending | azQ_1gTNH7k
3 | IMPROVE ONLINE READINESS AND CUSTOMER SATISFACTION | 3b | Retail integration | New from DPC Feb. 2023 | I. León | J. Fernández | UX/UI CUPRA Dealer pages | New from DPC Feb. 2023 | H1 2023 | Pending | g9QdEbB4GKQ
3 | IMPROVE ONLINE READINESS AND CUSTOMER SATISFACTION | 3b | Retail integration | New from DPC Feb. 2023 | I. León | J. Fernández | Development CUPRA Dealer pages | New from DPC Feb. 2023 | H2 2023 | Pending | 89n9raqMqGk
3 | IMPROVE ONLINE READINESS AND CUSTOMER SATISFACTION | 3b | Retail integration | New from DPC Feb. 2023 | I. León | J. Fernández | Rollout plan CUPRA Dealer pages | New from DPC Feb. 2023 | H2 2023 | Pending | LE3SP1oS4m0
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4a | One.Shop BtO (incl. FS AG sales products integration) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno | T. Garcia | ONE.Shop BtO: hold due to missing fundings on CARIAD side. Pending decision KVSK 23.05 | Started in 2022 | H1 2023 | Pending | ChENA045OeY
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4a | One.Shop BtO (incl. FS AG sales products integration) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno | T. Garcia | New payment method cash in FR: market has stopped customer go-live until leasing payment method is implemented. Go-live postponement currently being escalated on TMK level. | Started in 2022 | H1 2023 | Pending | gNbXePE-mxQ
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4a | One.Shop BtO (incl. FS AG sales products integration) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno | T. Garcia | UX/UI Improvements (pain points from 2022 analysis). | Started in 2022 | H1 2023 | Pending | wKPFocZrufo
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4a | One.Shop BtO (incl. FS AG sales products integration) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno | T. Garcia | Tacticals and discounts management (MVP Solution). | Started in 2022 | H1 2023 | Pending | HyIgXYdNCmU
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4a | One.Shop BtO (incl. FS AG sales products integration) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno | T. Garcia | Include Stock. | Started in 2022 | H2 2023 | Pending | dJs-PKK8gIw
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4a | One.Shop BtO (incl. FS AG sales products integration) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno | T. Garcia | UX/UI Improvements. | Started in 2022 | H2 2023 | Pending | c4cZsMuvoL0
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4a | One.Shop BtO (incl. FS AG sales products integration) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno | T. Garcia | Launch in SE TBC with CARIAD after fit-gap analysis: depending on current CARIAD funding situation. --> postponed to H1 2024 | Started in 2022 | H2 2023 | Pending | cHqznwOxtl0
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4a | One.Shop BtO (incl. FS AG sales products integration) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno | T. Garcia | New configuration experience (Zenit). | Started in 2022 | H2 2023 | Pending | DjqfYhp-SHA
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4a | One.Shop BtO (incl. FS AG sales products integration) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno | T. Garcia | Delivery time transparency. | Started in 2022 | H2 2023 | Pending | hl8Yh3Gfhsw
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4b | Stock (incl. ONE.Shop) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno / N. Medero | T. Garcia | [Stock locator Q1] CUPRA: Used Cars [DE], SEAT: Used Cars [DE] | Started in 2022 | H1 2023 | Done | VStWFDKE-4M
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4b | Stock (incl. ONE.Shop) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno / N. Medero | T. Garcia | [Stock locator Q1] Conversations with MX. DLV request already made. | Started in 2022 | H1 2023 | Pending | GonmGZdNy3s
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4b | Stock (incl. ONE.Shop) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno / N. Medero | T. Garcia | [Stock locator Q1] Analysis priorization of new requirements for used cars (DWA -->> CPO transition) | Started in 2022 | H1 2023 | Done | BW53ua29Tp0
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4b | Stock (incl. ONE.Shop) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno / N. Medero | T. Garcia | [Stock locator Q2] CUPRA: Used Cars [FR, SE] | Started in 2022 | H1 2023 | Pending | LYjTbDXZLAE
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4b | Stock (incl. ONE.Shop) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno / N. Medero | T. Garcia | [Stock locator Q2] CUPRA: New Cars [SE, FR delayed from Q1] | Started in 2022 | H1 2023 | Pending | GpcAbPiJQOo
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4b | Stock (incl. ONE.Shop) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno / N. Medero | T. Garcia | [Stock locator Q2] SEAT: New Cars [ES, UK, PL] | Started in 2022 | H1 2023 | Pending | KQs5OMkZXJY
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4b | Stock (incl. ONE.Shop) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno / N. Medero | T. Garcia | [Stock locator Q2] Analysis of capabilities to rollout in MX. Expected launch date Oct. 2023 | Started in 2022 | H1 2023 | Pending | hSitBI5xTrg
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4b | Stock (incl. ONE.Shop) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno / N. Medero | T. Garcia | [Stock locator Q2] UX/UI improvements: New PDP of CUPRA Stock LocatorStock Online Sales: | Started in 2022 | H1 2023 | Pending | KuwfMgEnudc
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4b | Stock (incl. ONE.Shop) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno / N. Medero | T. Garcia | [Stock Online Sales] SEAT New/Used cars: IT, CW21/23 (delayed from CW12/23) | Started in 2022 | H1 2023 | Pending | liSkfY0Lhac
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4b | Stock (incl. ONE.Shop) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno / N. Medero | T. Garcia | [Stock Online Sales] SEAT New/Used cars: FR (Cash), CW12/23: Market has stopped customer go-live until implementation of leasing (being escalated in group TMK level). | Started in 2022 | H1 2023 | Pending | xNiFmmR5dGE
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4b | Stock (incl. ONE.Shop) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno / N. Medero | T. Garcia | [Stock Online Sales] SEAT Used cars: DE, CW08/23 | Started in 2022 | H1 2023 | Done | wDGE1HZ1GR0
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4b | Stock (incl. ONE.Shop) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno / N. Medero | T. Garcia | [Stock Online Sales] UX/UI Improvements (pain points from 2022 analysis) | Started in 2022 | H1 2023 | Pending | FpR2Y6GoQIM
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4b | Stock (incl. ONE.Shop) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno / N. Medero | T. Garcia | [Stock Online Sales] Tacticals and discounts management (MVP Solution) | Started in 2022 | H1 2023 | Pending | z0SmBVsisiA
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4b | Stock (incl. ONE.Shop) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno / N. Medero | T. Garcia | [Stock locator Q3] CUPRA: New Cars [PL, IE, UK] - depending on market | Started in 2022 | H2 2023 | Pending | 0Rsdx-ZcUI4
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4b | Stock (incl. ONE.Shop) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno / N. Medero | T. Garcia | [Stock locator Q3] SEAT: New Cars [PL, IE, MX, UK] - depending on market-Q4 | Started in 2022 | H2 2023 | Pending | BsmwOlRyxHc
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4b | Stock (incl. ONE.Shop) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno / N. Medero | T. Garcia | [Stock locator Q4] CUPRA: New Cars [ES delayed from H1] - tentative | Started in 2022 | H2 2023 | Pending | yGeyJD0jp-c
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4b | Stock (incl. ONE.Shop) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno / N. Medero | T. Garcia | [Stock Online Sales] SEAT New/Used cars: ES (cash) | Started in 2022 | H2 2023 | Pending | PrZgyk19bWg
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4b | Stock (incl. ONE.Shop) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno / N. Medero | T. Garcia | [Stock Online Sales] CUPRA Used cars: FR, IT, DE, ES (Risk due to KVPS issues) | Started in 2022 | H2 2023 | Pending | _bqRjRdQcyA
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4b | Stock (incl. ONE.Shop) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno / N. Medero | T. Garcia | [Stock Online Sales] CUPRA New cars (Importer stock) : UK (Q4) | Started in 2022 | H2 2023 | Pending | oCgM1l8Gkvc
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4b | Stock (incl. ONE.Shop) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno / N. Medero | T. Garcia | [Stock Online Sales] UX/UI Improvements | Started in 2022 | H2 2023 | Pending | 61pHj8wBJlk
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4b | Stock (incl. ONE.Shop) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno / N. Medero | T. Garcia | [Stock Online Sales] Including Financing payment option (DE) | Started in 2022 | H2 2023 | Pending | EdXbh1BmfyU
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4b | Stock (incl. ONE.Shop) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno / N. Medero | T. Garcia | [Stock Online Sales] Develpment Refactor Stock Locator | Started in 2022 | H2 2023 | Pending | kvBCXSI3hqQ
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4b | Stock (incl. ONE.Shop) | H1 2022 Ongoing measure. Started in 2022 | J. Moreno / N. Medero | T. Garcia | [Stock Online Sales] Delivery time transparency | Started in 2022 | H2 2023 | Pending | _GoDq_L9qJw
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4c | Subscription | H1 2022 Ongoing measure. Started in 2022 | - | J. Fernández | Product ownership shifted to VF | Started in 2022 | H1 2023 | Done | w_Tx3MXmjrU
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4c | Subscription | H1 2022 Ongoing measure. Started in 2022 | - | J. Fernández | Requirements definition from VF side for digital integration | Started in 2022 | H2 2023 | Pending | TZs98VtTM9E
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4d | Agency model readiness - control updates with CUPRA offline readiness to ensure GS digital readiness | H2 2022 Ongoing measure. Started in 2022 | J. Zapatero | V. Monserrate | Follow-up on the project to ensure GS digital readiness | Started in 2022 | H1 2023 | Pending | Cpf1ftqJZ_4
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4d | Agency model readiness - control updates with CUPRA offline readiness to ensure GS digital readiness | H2 2022 Ongoing measure. Started in 2022 | J. Zapatero | V. Monserrate | Follow-up on the project to ensure GS digital readiness | Started in 2022 | H2 2023 | Pending | LFLgHL4WvSo
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4e | Tactical optimization (Intelligent Sales) | 2023 Ongoing measure. Started in 2022 | L. Kuprava | L. Kuprava | Implementation ramp up with different models and trims (March until Q3/23). Implementation started with tarraco for April campaign; | Started in 2022 | H1 2023 | Pending | fDWQEXcRaCg
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4e | Tactical optimization (Intelligent Sales) | 2023 Ongoing measure. Started in 2022 | L. Kuprava | L. Kuprava | Establish KPI's and results validation together with ES. | Started in 2022 | H1 2023 | Pending | gr9VsLlraRE
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4e | Tactical optimization (Intelligent Sales) | 2023 Ongoing measure. Started in 2022 | L. Kuprava | L. Kuprava | Implementation plan with DE under analysis; Kickoff and deep dive wokrshop with SEAT DEU done; Feedback meeting with management planned for CW22/23. | Started in 2022 | H1 2023 | Pending | 6j1F4AQdFwI
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4e | Tactical optimization (Intelligent Sales) | 2023 Ongoing measure. Started in 2022 | L. Kuprava | L. Kuprava | Extension of the project to CUPRA models (functionalities) | Started in 2022 | H2 2023 | Pending | JbtacJfIgEE
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4e | Tactical optimization (Intelligent Sales) | 2023 Ongoing measure. Started in 2022 | L. Kuprava | L. Kuprava | Validation for CUPRA models with ES | Started in 2022 | H2 2023 | Pending | LKipVD1jgnw
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4f | Used Car pricing tool | H2 2022 Delayed from 2022 | F. Amargant | F. Amargant | Delivery ES | Delayed from 2022 | H1 2023 | Done | -ikqACne8Ko
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4f | Used Car pricing tool | H2 2022 Delayed from 2022 | F. Amargant | F. Amargant | Exploration with DE (no interest shown) | Delayed from 2022 | H1 2023 | Done | 4Hvcu2Df2FM
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4f | Used Car pricing tool | H2 2022 Delayed from 2022 | F. Amargant | F. Amargant | Exploration with 1 more market | Delayed from 2022 | H2 2023 | Pending | apwlI-wiKGI
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4g | Stock/Mgmt. (Smart Order) | 2023 | S. Alvarez | S. Alvarez | Delivery of results of order list reccomenndation CUPRA ES 1. First delivery end of march 2023 with the recommendation for April 2023) | 2023 | H1 2023 | Done | jF9KSvR43Kk
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4g | Stock/Mgmt. (Smart Order) | 2023 | S. Alvarez | S. Alvarez | Exploration with markets (focus on DE)2. Presented Smart Order tool with management of DEU (scope, functionalities, live tool, roadmap, scalable plan)3. Next step: Technical team of DEU will come to BCN to guarantee the connections with CAP & understand better our data landscapeDelivery of results of order list recommendations CUPRA ES (Q1/23) | 2023 | H1 2023 | Pending | ZyzzPHZatbo
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4g | Stock/Mgmt. (Smart Order) | 2023 | S. Alvarez | S. Alvarez | Delivery of results of phase 2 ordering model for CUPRA ES (Q2/23) | 2023 | H2 2023 | Pending | G4u1iJDWciE
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4g | Stock/Mgmt. (Smart Order) | 2023 | S. Alvarez | S. Alvarez | Delivery of phase 2 CUPRA ES ordering model adding new constraints for CUPRA ES (Q4/23) | 2023 | H2 2023 | Pending | 0MqxQRgey_Q
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4h | 4.f. Australia solution as 360º sales workplace to 1-2 Markets | New from VSK Go-to-5% | M. Merino | M. Merino | Define a merge solution between current Spanish SA and AU solution. | New from VSK Go-to-5% | H1 2023 | Done | 4IfO_2YemTE
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4h | 4.f. Australia solution as 360º sales workplace to 1-2 Markets | New from VSK Go-to-5% | M. Merino | M. Merino | Select 2 countries candidates in order to implement de AU solution | New from VSK Go-to-5% | H1 2023 | Done | 5bEj1rYRXi4
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4h | 4.f. Australia solution as 360º sales workplace to 1-2 Markets | New from VSK Go-to-5% | M. Merino | M. Merino | Define the migration plan | New from VSK Go-to-5% | H1 2023 | Done | EWoQPtrTycA
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4h | 4.f. Australia solution as 360º sales workplace to 1-2 Markets | New from VSK Go-to-5% | M. Merino | M. Merino | Concept phase for the implementation in the first new market | New from VSK Go-to-5% | H1 2023 | Pending | jC85XQe8eng
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4h | 4.f. Australia solution as 360º sales workplace to 1-2 Markets | New from VSK Go-to-5% | M. Merino | M. Merino | Implementation phase and launch of the first market | New from VSK Go-to-5% | H2 2023 | Pending | 35KjX-VRFQM
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES | 4h | 4.f. Australia solution as 360º sales workplace to 1-2 Markets | New from VSK Go-to-5% | M. Merino | M. Merino | Implementation phase of the second market | New from VSK Go-to-5% | H2 2023 | Pending | 9qTudpVc6vw
5 | KEEP MOMENTUM | 5a | Order tracking | H1 2022 Ongoing measure. Started in 2022 | A. Jubero | T. Garcia | Improvements. | Started in 2022 | H1 2023 | Pending | _q47PdzyLJM
5 | KEEP MOMENTUM | 5a | Order tracking | H1 2022 Ongoing measure. Started in 2022 | A. Jubero | T. Garcia | Live in FR | Started in 2022 | H1 2023 | Done | HL-Y1NHKddo
5 | KEEP MOMENTUM | 5a | Order tracking | H1 2022 Ongoing measure. Started in 2022 | A. Jubero | T. Garcia | Rollout in ES (Q2/23) delayed from Q1 - tbd | Started in 2022 | H1 2023 | Pending | nSEMKD7s7xw
5 | KEEP MOMENTUM | 5a | Order tracking | H1 2022 Ongoing measure. Started in 2022 | A. Jubero | T. Garcia | Rollout in ITA (end Q2/23) | Started in 2022 | H1 2023 | Pending | J79ENVFdxFE
5 | KEEP MOMENTUM | 5a | Order tracking | H1 2022 Ongoing measure. Started in 2022 | A. Jubero | T. Garcia | Rollout in UK (end Q2/23) | Started in 2022 | H1 2023 | Pending | nv9VeTGzcMQ
5 | KEEP MOMENTUM | 5a | Order tracking | H1 2022 Ongoing measure. Started in 2022 | A. Jubero | T. Garcia | Reactivation in DE (tbd) | Started in 2022 | H1 2023 | Pending | tEPogkCewaE
5 | KEEP MOMENTUM | 5a | Order tracking | H1 2022 Ongoing measure. Started in 2022 | A. Jubero | T. Garcia | Reactivation in AUS (tbd) | Started in 2022 | H1 2023 | Pending | aeJxxpsFuJA
5 | KEEP MOMENTUM | 5a | Order tracking | H1 2022 Ongoing measure. Started in 2022 | A. Jubero | T. Garcia | Analytics insights about feature performance | Started in 2022 | H1 2023 | Pending | NLQ9sO9458k
5 | KEEP MOMENTUM | 5a | Order tracking | H1 2022 Ongoing measure. Started in 2022 | A. Jubero | T. Garcia | Rollout to other markets (tbd) | Started in 2022 | H2 2023 | Pending | B89oueBFShg
5 | KEEP MOMENTUM | 5a | Order tracking | H1 2022 Ongoing measure. Started in 2022 | A. Jubero | T. Garcia | Order tracking + delivery time | Started in 2022 | H2 2023 | Pending | Cs1XRb01ngs
5 | KEEP MOMENTUM | 5b | Select delivery in private area | 2023 | A. Jubero | T. Garcia | Scope 2023: New CUPRA customers can select the preferred car delivery mode in private area | 2023 | H1 2023 | Pending | Gs3vffB7-UU
5 | KEEP MOMENTUM | 5b | Select delivery in private area | 2023 | A. Jubero | T. Garcia | MVP for ES to be developed during PI2023.2 (tbd) | 2023 | H1 2023 | Pending | R0phX4PLNpo
5 | KEEP MOMENTUM | 5b | Select delivery in private area | 2023 | A. Jubero | T. Garcia | Analyze MVP results for further rollout to other markets | 2023 | H2 2023 | Pending | Od0EGHrSF9w
5 | KEEP MOMENTUM | 5c | Waiting experiences (promote action model) | H1 2022 Ongoing measure. Started in 2022 | M. Gómez | T. Garcia | Build a plan for rolling it out in car configurator to other markets-> Current supply situation critical to ensure available configurations. | Started in 2022 | H1 2023 | Pending | dhKMhMiFXmo
5 | KEEP MOMENTUM | 5c | Waiting experiences (promote action model) | H1 2022 Ongoing measure. Started in 2022 | M. Gómez | T. Garcia | Launch specific closed type in eShop in ES to increase coversions (BtO solution to be used). | Started in 2022 | H1 2023 | Done | 4Mc0mATiVhk
5 | KEEP MOMENTUM | 5c | Waiting experiences (promote action model) | H1 2022 Ongoing measure. Started in 2022 | M. Gómez | T. Garcia | Rollout to other markets (depending on plan results) | Started in 2022 | H2 2023 | Pending | VEGJzFUWHR8
5 | KEEP MOMENTUM | 5c | Waiting experiences (promote action model) | H1 2022 Ongoing measure. Started in 2022 | M. Gómez | T. Garcia | Launch specific closed type in eShop in DE to increase coversions (BtO solution to be used). | Started in 2022 | H2 2023 | Pending | irCqYv1vOk8
6 | IMPROVE ENROLLMENT RATE TO IMPROVE BUSINESS POTENTIAL VIA | 6a | Pre-Enrollment process | H2 2022 Ongoing measure. Started in 2022 | L. Giménez | L. Giménez | Deep-link OCW integration (CW 04/23) | Started in 2022 | H1 2023 | Done | StX3bxJ3KSo
6 | IMPROVE ENROLLMENT RATE TO IMPROVE BUSINESS POTENTIAL VIA | 6a | Pre-Enrollment process | H2 2022 Ongoing measure. Started in 2022 | L. Giménez | L. Giménez | Multiple cars (Descoped to 2024 to minimize 2023 costs) | Started in 2022 | H1 2023 | Pending | zMgBnL8nDPA
6 | IMPROVE ENROLLMENT RATE TO IMPROVE BUSINESS POTENTIAL VIA | 6a | Pre-Enrollment process | H2 2022 Ongoing measure. Started in 2022 | L. Giménez | L. Giménez | Used cars (Descoped to 2024 to minimize 2023 costs) | Started in 2022 | H1 2023 | Pending | _rwxZLS3Y04
6 | IMPROVE ENROLLMENT RATE TO IMPROVE BUSINESS POTENTIAL VIA | 6a | Pre-Enrollment process | H2 2022 Ongoing measure. Started in 2022 | L. Giménez | L. Giménez | Online sales (delayed from H1) | Started in 2022 | H2 2023 | Pending | x_OvTHrxjaI
6 | IMPROVE ENROLLMENT RATE TO IMPROVE BUSINESS POTENTIAL VIA | 6a | Pre-Enrollment process | H2 2022 Ongoing measure. Started in 2022 | L. Giménez | L. Giménez | Modify consent (delayed from H1) | Started in 2022 | H2 2023 | Pending | _vtbyh-YsbM
6 | IMPROVE ENROLLMENT RATE TO IMPROVE BUSINESS POTENTIAL VIA | 6a | Pre-Enrollment process | H2 2022 Ongoing measure. Started in 2022 | L. Giménez | L. Giménez | Improved Customer Journey (delayed from H1) | Started in 2022 | H2 2023 | Pending | JnO--cuxeB4
6 | IMPROVE ENROLLMENT RATE TO IMPROVE BUSINESS POTENTIAL VIA | 6a | Pre-Enrollment process | H2 2022 Ongoing measure. Started in 2022 | L. Giménez | L. Giménez | Integrated user manual (cw48/23) | Started in 2022 | H2 2023 | Pending | ZBGQeSKnfQA
6 | IMPROVE ENROLLMENT RATE TO IMPROVE BUSINESS POTENTIAL VIA | 6a | Pre-Enrollment process | H2 2022 Ongoing measure. Started in 2022 | L. Giménez | L. Giménez | Primary User prenomination (cw48/23) | Started in 2022 | H2 2023 | Pending | U5Mvoj382SA
6 | IMPROVE ENROLLMENT RATE TO IMPROVE BUSINESS POTENTIAL VIA | 6a | Pre-Enrollment process | H2 2022 Ongoing measure. Started in 2022 | L. Giménez | L. Giménez | VIN from Commission. Nr (delayed from H1, depending on IT) | Started in 2022 | H2 2023 | Pending | d6PyspP3BGw
6 | IMPROVE ENROLLMENT RATE TO IMPROVE BUSINESS POTENTIAL VIA | 6b | Set-Up-assistant | 2023 | M. Navarrete | L. Giménez | CUPRA Concept ready (Flow, Screens, etc). | 2023 | H1 2023 | Done | O0cgboDQiKY
6 | IMPROVE ENROLLMENT RATE TO IMPROVE BUSINESS POTENTIAL VIA | 6b | Set-Up-assistant | 2023 | M. Navarrete | L. Giménez | User tensting. | 2023 | H1 2023 | Pending | b6zz76kcmB0
6 | IMPROVE ENROLLMENT RATE TO IMPROVE BUSINESS POTENTIAL VIA | 6b | Set-Up-assistant | 2023 | M. Navarrete | L. Giménez | Alignment with rest of Group Brands (CW05-CW19/23). | 2023 | H1 2023 | Done | cunFzwNOVfU
6 | IMPROVE ENROLLMENT RATE TO IMPROVE BUSINESS POTENTIAL VIA | 6b | Set-Up-assistant | 2023 | M. Navarrete | L. Giménez | Priorization in CARIAD PI. | 2023 | H1 2023 | Pending | yRRZ38Iuslk
6 | IMPROVE ENROLLMENT RATE TO IMPROVE BUSINESS POTENTIAL VIA | 6b | Set-Up-assistant | 2023 | M. Navarrete | L. Giménez | Launch Set-up Assistant in MyCUPRA App | 2023 | H2 2023 | Pending | GneuzaDnylg
6 | IMPROVE ENROLLMENT RATE TO IMPROVE BUSINESS POTENTIAL VIA | 6b | Set-Up-assistant | 2023 | M. Navarrete | L. Giménez | Inclusion as Scope for SEAT OLA | 2023 | H2 2023 | Pending | uDX2GYvPQuw
6 | IMPROVE ENROLLMENT RATE TO IMPROVE BUSINESS POTENTIAL VIA | 6c | UX enrolment | New from DPC Feb. 2023 | A. Solves (apps) / EE (in-car) | L. Giménez | Audit to identify wording improvements. | New from DPC Feb. 2023 | H1 2023 | Done | FBVJPBZqlQI
6 | IMPROVE ENROLLMENT RATE TO IMPROVE BUSINESS POTENTIAL VIA | 6c | UX enrolment | New from DPC Feb. 2023 | A. Solves (apps) / EE (in-car) | L. Giménez | Posibility to add VIN with the camera (scan). | New from DPC Feb. 2023 | H1 2023 | Pending | 4Iw0lxBgZ_E
6 | IMPROVE ENROLLMENT RATE TO IMPROVE BUSINESS POTENTIAL VIA | 6c | UX enrolment | New from DPC Feb. 2023 | A. Solves (apps) / EE (in-car) | L. Giménez | Reduction of the screens (legal acceptance screens). | New from DPC Feb. 2023 | H1 2023 | Pending | tW243SsLnyY
6 | IMPROVE ENROLLMENT RATE TO IMPROVE BUSINESS POTENTIAL VIA | 6c | UX enrolment | New from DPC Feb. 2023 | A. Solves (apps) / EE (in-car) | L. Giménez | New onboarding screens. | New from DPC Feb. 2023 | H1 2023 | Pending | JapEyu6p0YE
6 | IMPROVE ENROLLMENT RATE TO IMPROVE BUSINESS POTENTIAL VIA | 6c | UX enrolment | New from DPC Feb. 2023 | A. Solves (apps) / EE (in-car) | L. Giménez | New splash screen. | New from DPC Feb. 2023 | H1 2023 | Done | gTiXLOr6qWE
6 | IMPROVE ENROLLMENT RATE TO IMPROVE BUSINESS POTENTIAL VIA | 6c | UX enrolment | New from DPC Feb. 2023 | A. Solves (apps) / EE (in-car) | L. Giménez | Implementation of wording improvements | New from DPC Feb. 2023 | H2 2023 | Pending | fUCD5VjrkU4
6 | IMPROVE ENROLLMENT RATE TO IMPROVE BUSINESS POTENTIAL VIA | 6c | UX enrolment | New from DPC Feb. 2023 | A. Solves (apps) / EE (in-car) | L. Giménez | Improve "where to find VIN" screen | New from DPC Feb. 2023 | H2 2023 | Pending | re75z6NJWyw
7 | BE E-MOB READY VIA | 7a | Charging Services | H1 2022 Ongoing measure. Started in 2022 | M. Navarrete (MyCUPRA) A. Jubero (web) | A. Rivera | [Business] Markets: UK MSP launch, incl. vouchers (end Q1) | Started in 2022 | H1 2023 | Done | a5RUIp2hS9w
7 | BE E-MOB READY VIA | 7a | Charging Services | H1 2022 Ongoing measure. Started in 2022 | M. Navarrete (MyCUPRA) A. Jubero (web) | A. Rivera | [Business] Vouchers (planned): Follow-up launch in ES, SE, IT | Started in 2022 | H1 2023 | Done | LW0oViy3LX0
7 | BE E-MOB READY VIA | 7a | Charging Services | H1 2022 Ongoing measure. Started in 2022 | M. Navarrete (MyCUPRA) A. Jubero (web) | A. Rivera | [Business]Development to be finished in H2 2023 | Started in 2022 | H1 2023 | Pending | ZfIDT_6FDWE
7 | BE E-MOB READY VIA | 7a | Charging Services | H1 2022 Ongoing measure. Started in 2022 | M. Navarrete (MyCUPRA) A. Jubero (web) | A. Rivera | [In-car] Launch in-car app | Started in 2022 | H2 2023 | Pending | SX1z3esDN3o
7 | BE E-MOB READY VIA | 7a | Charging Services | H1 2022 Ongoing measure. Started in 2022 | M. Navarrete (MyCUPRA) A. Jubero (web) | A. Rivera | [Out-car] MSP Integration in MyCUPRA App live | Started in 2022 | H2 2023 | Pending | 8SphWHyDyOk
7 | BE E-MOB READY VIA | 7a | Charging Services | H1 2022 Ongoing measure. Started in 2022 | M. Navarrete (MyCUPRA) A. Jubero (web) | A. Rivera | [Out-car] MSP Feature app (web / private area) launch | Started in 2022 | H2 2023 | Pending | YkmRn8Uy0ek
7 | BE E-MOB READY VIA | 7a | Charging Services | H1 2022 Ongoing measure. Started in 2022 | M. Navarrete (MyCUPRA) A. Jubero (web) | A. Rivera | [Business] Markets: Norway MSP launch (end Q4) | Started in 2022 | H2 2023 | Pending | oqjnIeU9VYE
7 | BE E-MOB READY VIA | 7b | EV Route planning | 2023 | M. Navarrete (MyCUPRA) / I. Leon (Web) | A. Rivera | Approve (DPC 21.02) the way forward for EV Route planner in 2023 (Goal achieved with epic LPM-187 for PI23.2) | 2023 | H1 2023 | Done | J0ZEbgEQrlw
7 | BE E-MOB READY VIA | 7b | EV Route planning | 2023 | M. Navarrete (MyCUPRA) / I. Leon (Web) | A. Rivera | Development to be finished in H2 2023 | 2023 | H1 2023 | Pending | bvZph1EQasE
7 | BE E-MOB READY VIA | 7b | EV Route planning | 2023 | M. Navarrete (MyCUPRA) / I. Leon (Web) | A. Rivera | Launch EV Route planner with CARIAD for UNECE (cw50/23). | 2023 | H2 2023 | Pending | DUpMFKcew90
7 | BE E-MOB READY VIA | 7b | EV Route planning | 2023 | M. Navarrete (MyCUPRA) / I. Leon (Web) | A. Rivera | Launch EV Route planner in Web | 2023 | H2 2023 | Pending | LwUBGdP2aro
7 | BE E-MOB READY VIA | 7c | Battery Education | 2023 | A. Jubero / M. Navarrete / E. Parrilla | A. Rivera | Learning center in App (Community scope): Delayed in DPC 21.02 due to repriorization. | 2023 | H1 2023 | Pending | ixeEvZU3jWM
7 | BE E-MOB READY VIA | 7c | Battery Education | 2023 | A. Jubero / M. Navarrete / E. Parrilla | A. Rivera | Analyze metrics of implemented measures | 2023 | H2 2023 | Pending | k0NrKhbf3kM
7 | BE E-MOB READY VIA | 7c | Battery Education | 2023 | A. Jubero / M. Navarrete / E. Parrilla | A. Rivera | Learning center in App (Community scope): Education pills for charging processes & issues, including battery charging & care (delayed from H1) | 2023 | H2 2023 | Pending | nB4mpsSCBYM
8 | EXTEND BUSINESS & MONETIZE VIA | 8a | Loyalty products within private area / app | H1 2022 Ongoing measure. Started in 2022 | A. Jubero (Private area) / I. Leon (Web) / M. Gomez (One marketplace) / E. Parrilla (App) | E. Ortiz | [Loyalty products. Private Area (from FoA 8d)] FS Local: Australia Go live (in PI pending tasks from market). | Started in 2022 | H1 2023 | Pending | z68Y5GZ0DeQ
8 | EXTEND BUSINESS & MONETIZE VIA | 8a | Loyalty products within private area / app | H1 2022 Ongoing measure. Started in 2022 | A. Jubero (Private area) / I. Leon (Web) / M. Gomez (One marketplace) / E. Parrilla (App) | E. Ortiz | [Loyalty products. Private Area (from FoA 8d)] VWFS products: Design proposal and development. | Started in 2022 | H1 2023 | Done | 6a4s_3cXWcs
8 | EXTEND BUSINESS & MONETIZE VIA | 8a | Loyalty products within private area / app | H1 2022 Ongoing measure. Started in 2022 | A. Jubero (Private area) / I. Leon (Web) / M. Gomez (One marketplace) / E. Parrilla (App) | E. Ortiz | [Loyalty products. Private Area (from FoA 8d)] VWFS products: DE Rollout | Started in 2022 | H1 2023 | Pending | -tQC33zF6DM
8 | EXTEND BUSINESS & MONETIZE VIA | 8a | Loyalty products within private area / app | H1 2022 Ongoing measure. Started in 2022 | A. Jubero (Private area) / I. Leon (Web) / M. Gomez (One marketplace) / E. Parrilla (App) | E. Ortiz | [Loyalty products. App (from 8d)] Feature development | Started in 2022 | H1 2023 | Done | zKSQcf2GKU0
8 | EXTEND BUSINESS & MONETIZE VIA | 8a | Loyalty products within private area / app | H1 2022 Ongoing measure. Started in 2022 | A. Jubero (Private area) / I. Leon (Web) / M. Gomez (One marketplace) / E. Parrilla (App) | E. Ortiz | [Loyalty products. App (from 8d)] MVP in DE: Maintenance, Warranty & Insurance financial products | Started in 2022 | H1 2023 | Done | zwUbLKGGs1A
8 | EXTEND BUSINESS & MONETIZE VIA | 8a | Loyalty products within private area / app | H1 2022 Ongoing measure. Started in 2022 | A. Jubero (Private area) / I. Leon (Web) / M. Gomez (One marketplace) / E. Parrilla (App) | E. Ortiz | [Loyalty products. App (from 8d)] App release 1.9 (CW20/23) | Started in 2022 | H1 2023 | Pending | pUFeuSnoeWY
8 | EXTEND BUSINESS & MONETIZE VIA | 8a | Loyalty products within private area / app | H1 2022 Ongoing measure. Started in 2022 | A. Jubero (Private area) / I. Leon (Web) / M. Gomez (One marketplace) / E. Parrilla (App) | E. Ortiz | [Accesories] Service design of visibility improvements | Started in 2022 | H1 2023 | Pending | FIBh86PcibQ
8 | EXTEND BUSINESS & MONETIZE VIA | 8a | Loyalty products within private area / app | H1 2022 Ongoing measure. Started in 2022 | A. Jubero (Private area) / I. Leon (Web) / M. Gomez (One marketplace) / E. Parrilla (App) | E. Ortiz | [Accesories] Service design of Integration of AS products in the "One market place" strategy. | Started in 2022 | H1 2023 | Pending | CLvXNTJUUxE
8 | EXTEND BUSINESS & MONETIZE VIA | 8a | Loyalty products within private area / app | H1 2022 Ongoing measure. Started in 2022 | A. Jubero (Private area) / I. Leon (Web) / M. Gomez (One marketplace) / E. Parrilla (App) | E. Ortiz | [Loyalty products. Private Area (from FoA 8d)] Live markets: Follow-up | Started in 2022 | H2 2023 | Pending | YLOYMYm_FNs
8 | EXTEND BUSINESS & MONETIZE VIA | 8a | Loyalty products within private area / app | H1 2022 Ongoing measure. Started in 2022 | A. Jubero (Private area) / I. Leon (Web) / M. Gomez (One marketplace) / E. Parrilla (App) | E. Ortiz | [Loyalty products. Private Area (from FoA 8d)] VWFS products: Roll Out in new markets (IE, FR, IT + TBC) | Started in 2022 | H2 2023 | Pending | Wy9iJgGSBYg
8 | EXTEND BUSINESS & MONETIZE VIA | 8a | Loyalty products within private area / app | H1 2022 Ongoing measure. Started in 2022 | A. Jubero (Private area) / I. Leon (Web) / M. Gomez (One marketplace) / E. Parrilla (App) | E. Ortiz | [Loyalty products. App (from 8d)] Rollout to other markets (pending rollout from VWFS) | Started in 2022 | H2 2023 | Pending | EIQYF6Ym79w
8 | EXTEND BUSINESS & MONETIZE VIA | 8a | Loyalty products within private area / app | H1 2022 Ongoing measure. Started in 2022 | A. Jubero (Private area) / I. Leon (Web) / M. Gomez (One marketplace) / E. Parrilla (App) | E. Ortiz | [Accesories] Implementation of visibility improvements | Started in 2022 | H2 2023 | Pending | nqtmN2weQyc
8 | EXTEND BUSINESS & MONETIZE VIA | 8a | Loyalty products within private area / app | H1 2022 Ongoing measure. Started in 2022 | A. Jubero (Private area) / I. Leon (Web) / M. Gomez (One marketplace) / E. Parrilla (App) | E. Ortiz | [Accesories] Implementation of AS products in "One market place" | Started in 2022 | H2 2023 | Pending | yQbBN6XQhuc
8 | EXTEND BUSINESS & MONETIZE VIA | 8a | Loyalty products within private area / app | H1 2022 Ongoing measure. Started in 2022 | A. Jubero (Private area) / I. Leon (Web) / M. Gomez (One marketplace) / E. Parrilla (App) | E. Ortiz | [AS Offers] Service design of Integration of tailored AS Offer section in all frontends | Started in 2022 | H2 2023 | Pending | g3-W-YeQynY
8 | EXTEND BUSINESS & MONETIZE VIA | 8d | Predictive Maintenance | H1 2022 | M. Navarrete (App) / EE (Web-App) | S. Rejas | OVM Web-App pre instalation (pre-installation feasiblity only from UNECE - Tavascan CW50/23) | H1 2022 | H1 2023 | Pending | do7HQ4-4RKA
8 | EXTEND BUSINESS & MONETIZE VIA | 8d | Predictive Maintenance | H1 2022 | M. Navarrete (App) / EE (Web-App) | S. Rejas | Integration "Warning lights + Book an appointment" in MyCUPRA App MOD3 ' (delay from H1 due to app scope) | H1 2022 | H2 2023 | Pending | 8efxufGKp44
8 | EXTEND BUSINESS & MONETIZE VIA | 8d | Predictive Maintenance | H1 2022 | M. Navarrete (App) / EE (Web-App) | S. Rejas | Launch PrM Web-App for MOD3 (depending on CARIAD repriorisation) (delayed from H1) | H1 2022 | H2 2023 | Pending | Tunt3paJjcY
8 | EXTEND BUSINESS & MONETIZE VIA | 8d | Predictive Maintenance | H1 2022 | M. Navarrete (App) / EE (Web-App) | S. Rejas | Ensure readiness for PrM Web-App / App level2 (depending on CARIAD repriorisation), to be launched in 2024 | H1 2022 | H2 2023 | Pending | GUq7WARlH98
8 | EXTEND BUSINESS & MONETIZE VIA | 8d | Predictive Maintenance | H1 2022 | M. Navarrete (App) / EE (Web-App) | S. Rejas | OVM Web-App pre instalation (go live dependent on GL - dealyed from H1) | H1 2022 | H2 2023 | Pending | pDa7SpOllVQ
8 | EXTEND BUSINESS & MONETIZE VIA | 8e | Connected B2B/Fleet Services | 2023 Ongoing measure. Started in 2022 | EE, FS | P. Martinez | [Fleet Data API] Presentation in DPC (June'23) for approval of 2nd wave of "Vehicle Data Access" featuresConnect PRO | Started in 2022 | H1 2023 | Pending | DcK9ifM-rcs
11 | MyCUPRA APP AS MAIN DIGITAL PLATFORM FOR OWNERS | 8e | Connected B2B/Fleet Services | 2023 Ongoing measure. Started in 2022 | EE, FS | P. Martinez | [Connect PRO] Project presentation for decision once Financial model via Licenses is clarified withing brands and CARIAD in end of March.-> Project presentation for VW has been delayed to end of May. | Started in 2022 | H1 2023 | Pending | tktd6TFw6-c
11 | MyCUPRA APP AS MAIN DIGITAL PLATFORM FOR OWNERS | 8e | Connected B2B/Fleet Services | 2023 Ongoing measure. Started in 2022 | EE, FS | P. Martinez | [Fleet Data API] Launch in cw52/23. | Started in 2022 | H2 2023 | Pending | 7cuFJn_8s9c
11 | MyCUPRA APP AS MAIN DIGITAL PLATFORM FOR OWNERS | 8e | Connected B2B/Fleet Services | 2023 Ongoing measure. Started in 2022 | EE, FS | P. Martinez | [Connect PRO] TBD depending on decision. | Started in 2022 | H2 2023 | Pending | FD5AmyIhFk8
11 | MyCUPRA APP AS MAIN DIGITAL PLATFORM FOR OWNERS | 8f | Expand Features / Functions in MyCUPRA App (excl. initiatives in other FoA) | H2 2022 & 2023 Ongoing measure. Started in 2022 | E. Parrilla / M. Navarrete | M. Maristany / A. Rivera / S. Rejas | [MyCUPRA Widget] Introduced in PI 2023.1 (UX & technical spike to be delivered by end of PI 2023.1) | Started in 2022 | H1 2023 | Done | EUAO8-6EnIE
11 | MyCUPRA APP AS MAIN DIGITAL PLATFORM FOR OWNERS | 8f | Expand Features / Functions in MyCUPRA App (excl. initiatives in other FoA) | H2 2022 & 2023 Ongoing measure. Started in 2022 | E. Parrilla / M. Navarrete | M. Maristany / A. Rivera / S. Rejas | [MyCUPRA Widget] To be developed in PI 23.2 | Started in 2022 | H1 2023 | Pending | AWj8IMXBFuE
11 | MyCUPRA APP AS MAIN DIGITAL PLATFORM FOR OWNERS | 8f | Expand Features / Functions in MyCUPRA App (excl. initiatives in other FoA) | H2 2022 & 2023 Ongoing measure. Started in 2022 | E. Parrilla / M. Navarrete | M. Maristany / A. Rivera / S. Rejas | [MyCUPRA Widget] To be launched in next release 1.10.0 (Q2/23) | Started in 2022 | H1 2023 | Pending | CE5Gp6Yn3gU
11 | MyCUPRA APP AS MAIN DIGITAL PLATFORM FOR OWNERS | 8f | Expand Features / Functions in MyCUPRA App (excl. initiatives in other FoA) | H2 2022 & 2023 Ongoing measure. Started in 2022 | E. Parrilla / M. Navarrete | M. Maristany / A. Rivera / S. Rejas | [Cost Monitor] To be launched in next release 1.8.0 (Q1/23) | Started in 2022 | H1 2023 | Done | lhIgs2ov2Is
12 | IMPROVE DATA BUSINESS VIA | 8f | Expand Features / Functions in MyCUPRA App (excl. initiatives in other FoA) | H2 2022 & 2023 Ongoing measure. Started in 2022 | E. Parrilla / M. Navarrete | M. Maristany / A. Rivera / S. Rejas | [Parking use case] MVP for Parking service development based on Skoda solution - Approval of Way Forward | Started in 2022 | H1 2023 | Pending | V1EHhDV3qqU
12 | IMPROVE DATA BUSINESS VIA | 8f | Expand Features / Functions in MyCUPRA App (excl. initiatives in other FoA) | H2 2022 & 2023 Ongoing measure. Started in 2022 | E. Parrilla / M. Navarrete | M. Maristany / A. Rivera / S. Rejas | [CONNECT] Plan definition on how wich features could enrich the portfolio | Started in 2022 | H1 2023 | Pending | 1VxHZE8lrM8
12 | IMPROVE DATA BUSINESS VIA | 8f | Expand Features / Functions in MyCUPRA App (excl. initiatives in other FoA) | H2 2022 & 2023 Ongoing measure. Started in 2022 | E. Parrilla / M. Navarrete | M. Maristany / A. Rivera / S. Rejas | [After sales] After sales CX analysis for prospect, owner and renting customer | Started in 2022 | H1 2023 | Pending | ZY-SlAnFS0I
12 | IMPROVE DATA BUSINESS VIA | 8f | Expand Features / Functions in MyCUPRA App (excl. initiatives in other FoA) | H2 2022 & 2023 Ongoing measure. Started in 2022 | E. Parrilla / M. Navarrete | M. Maristany / A. Rivera / S. Rejas | [Parking use case] Integration (target Q4/23) in MyCUPRA App if prioritized in PI | Started in 2022 | H2 2023 | Pending | MRLTh5Ys2cM
12 | IMPROVE DATA BUSINESS VIA | 8f | Expand Features / Functions in MyCUPRA App (excl. initiatives in other FoA) | H2 2022 & 2023 Ongoing measure. Started in 2022 | E. Parrilla / M. Navarrete | M. Maristany / A. Rivera / S. Rejas | [CONNECT] MOD4 UNECE 100% for cw48/23 in MyCUPRA App. | Started in 2022 | H2 2023 | Pending | 9z6VyE2IsPQ
12 | IMPROVE DATA BUSINESS VIA | 8f | Expand Features / Functions in MyCUPRA App (excl. initiatives in other FoA) | H2 2022 & 2023 Ongoing measure. Started in 2022 | E. Parrilla / M. Navarrete | M. Maristany / A. Rivera / S. Rejas | [After sales] Service design: digital repair experience (starting with integration of Service CAM) | Started in 2022 | H2 2023 | Pending | 7M0KWTW3mDY
12 | IMPROVE DATA BUSINESS VIA | 8f | Expand Features / Functions in MyCUPRA App (excl. initiatives in other FoA) | H2 2022 & 2023 Ongoing measure. Started in 2022 | E. Parrilla / M. Navarrete | M. Maristany / A. Rivera / S. Rejas | [After sales] Make My CUPRA APP available for non-connected customers | Started in 2022 | H2 2023 | Pending | XPnBf54VAFU
12 | IMPROVE DATA BUSINESS VIA | 8f | Expand Features / Functions in MyCUPRA App (excl. initiatives in other FoA) | H2 2022 & 2023 Ongoing measure. Started in 2022 | E. Parrilla / M. Navarrete | M. Maristany / A. Rivera / S. Rejas | [After sales] Display personalized AS information and content (next maintenance, warranty information, car history,…) (delayed from H1) | Started in 2022 | H2 2023 | Pending | NbNV66BuqsI
12 | IMPROVE DATA BUSINESS VIA | 8g | OTA Updates | New from VSK Go-to-5% | VA / EE | VA | From GS: Follow-up on the project to ensure GS digital readiness, if needed | New from VSK Go-to-5% | H1 2023 | Pending | YKIfX-5pmfY
12 | IMPROVE DATA BUSINESS VIA | 8g | OTA Updates | New from VSK Go-to-5% | VA / EE | VA | From GS: Follow-up on the project to ensure GS digital readiness, if needed | New from VSK Go-to-5% | H2 2023 | Pending | c50RCheHtIs
9 | INCREASE LOYALTY AND REDUCE EFFORTS TO CONQUER | 9a | Digital renewal (incl. 5d FS AG sales products integration) | H2 2022 Ongoing measure. Started in 2022 | R. Vitorio | R. Vitorio | DE took the task to define a global blueprint together with SEAT/CUPRA HQ and VWFS for a digital renewal journey to increase the rates across the markets. A set of use cases were defined then prioritized and the roll-out will be based on DE case and then scaled to other markets. Prioritized use cases:- Matchmaker Maturity Levels- Renewal Cascading- E-Commerce- Brand Portal IntegrationOn top, a FS data transfer plus the Km information from HQ use case will be tested for ES in order to complete the blueprint | Started in 2022 | H1 2023 | Pending | 6uQxxwkLfWE
9 | INCREASE LOYALTY AND REDUCE EFFORTS TO CONQUER | 9a | Digital renewal (incl. 5d FS AG sales products integration) | H2 2022 Ongoing measure. Started in 2022 | R. Vitorio | R. Vitorio | Use cases development | Started in 2022 | H2 2023 | Pending | z0wl_42ii04
9 | INCREASE LOYALTY AND REDUCE EFFORTS TO CONQUER | 9b | CUPRA Passport | 2023 | M. Palma | M. Palma | Launch MVP in ES (integration in Private area) | 2023 | H1 2023 | Pending | rHU5QtZ-pyw
9 | INCREASE LOYALTY AND REDUCE EFFORTS TO CONQUER | 9b | CUPRA Passport | 2023 | M. Palma | M. Palma | Extend Features (Certificate as NFT, Estimate vehicle current Market Value, Maintanance & Repair History) | 2023 | H2 2023 | Pending | Wn8pPD0ZV3g
9 | INCREASE LOYALTY AND REDUCE EFFORTS TO CONQUER | 9b | CUPRA Passport | 2023 | M. Palma | M. Palma | Extend rollout to other Markets (DE, FR, UK, CH) | 2023 | H2 2023 | Pending | jmY75WxkRF4
9 | INCREASE LOYALTY AND REDUCE EFFORTS TO CONQUER | 9b | CUPRA Passport | 2023 | M. Palma | M. Palma | Integration in MyCupra App | 2023 | H2 2023 | Pending | 0lyzWgwrOXc
9 | INCREASE LOYALTY AND REDUCE EFFORTS TO CONQUER | 9c | Community | 2023 Ongoing measure. Started in 2022 | R. Vitorio | R. Vitorio | Approval of CUPRA Community Target Picture, MVP Definition & Governance (Q1/23) | Started in 2022 | H1 2023 | Done | n4HTZZNXdrQ
9 | INCREASE LOYALTY AND REDUCE EFFORTS TO CONQUER | 9c | Community | 2023 Ongoing measure. Started in 2022 | R. Vitorio | R. Vitorio | MVP Approval and refinement: Customer Data assessment, CRM, App and Private area requirements definition | Started in 2022 | H1 2023 | Done | dwhSv1qqOwM
9 | INCREASE LOYALTY AND REDUCE EFFORTS TO CONQUER | 9c | Community | 2023 Ongoing measure. Started in 2022 | R. Vitorio | R. Vitorio | Start of MVP Development | Started in 2022 | H1 2023 | Pending | 7TgkFQIO46M
9 | INCREASE LOYALTY AND REDUCE EFFORTS TO CONQUER | 9c | Community | 2023 Ongoing measure. Started in 2022 | R. Vitorio | R. Vitorio | MVP Development | Started in 2022 | H2 2023 | Pending | xHJ2sw9AOzw
9 | INCREASE LOYALTY AND REDUCE EFFORTS TO CONQUER | 9c | Community | 2023 Ongoing measure. Started in 2022 | R. Vitorio | R. Vitorio | MVP launch | Started in 2022 | H2 2023 | Pending | Hy6qhYJwZBc
13 | DIGITAL HUB | 13 |  | New from DPC Feb. 2023 | I. Partal from CODE | D. Mesa | Current Digital agency extension until end May for GS-D / end of June for VM (Model Year content) | New from DPC Feb. 2023 | H1 2023 | Done | b_hKw0NdyV0
13 | DIGITAL HUB | 13 |  | New from DPC Feb. 2023 | I. Partal from CODE | D. Mesa | Digital agency nomination 1st week June (tomorrow 01.06 at Group CSC), one single agency from July | New from DPC Feb. 2023 | H1 2023 | Pending | RpwplnQ3D3o
13 | DIGITAL HUB | 13 |  | New from DPC Feb. 2023 | I. Partal from CODE | D. Mesa | One.Team governance model definition & communication | New from DPC Feb. 2023 | H1 2023 | Pending | AO3a1dimUJ8
13 | DIGITAL HUB | 13 |  | New from DPC Feb. 2023 | I. Partal from CODE | D. Mesa | PO roles migration (waves March / June / Sep / Sep'24) | New from DPC Feb. 2023 | H1 2023 | Pending | qoq3y9AiIU4
13 | DIGITAL HUB | 13 |  | New from DPC Feb. 2023 | I. Partal from CODE | D. Mesa | One.Team implementation | New from DPC Feb. 2023 | H2 2023 | Pending | J3cflNrmLTU
13 | DIGITAL HUB | 13 |  | New from DPC Feb. 2023 | I. Partal from CODE | D. Mesa | PO roles migration (waves March / June / Sep / Sep'24) | New from DPC Feb. 2023 | H2 2023 | Pending | 6-Cuc8ZXw8k

## Sheet2
1 | INCREASE CONVERSION RATE VIA
2 | INCREASE CALL-TO-ACTION RATE VIA
2 | INCREASE CALL-TO-ACTION RATE VIA
3 | IMPROVE ONLINE READINESS AND CUSTOMER SATISFACTION
4 | REDUCE SALES COSTS AND PREVENT VOLUME LOSSES
5 | KEEP MOMENTUM
6 | IMPROVE ENROLLMENT RATE TO IMPROVE BUSINESS POTENTIAL VIA
7 | BE E-MOB READY VIA
8 | EXTEND BUSINESS & MONETIZE VIA
9 | INCREASE LOYALTY AND REDUCE EFFORTS TO CONQUER
10 | SEAMLESS JOURNE, DIGITAL BUSINESS AND AGENCY MODEL READINESS
11 | MyCUPRA APP AS MAIN DIGITAL PLATFORM FOR OWNERS
12 | IMPROVE DATA BUSINESS VIA
13 | DIGITAL HUB